## Invoices
Contract with Luminary Publishing, Inc.
2018 Business Attraction Marketing
4/1/2018 - 12/31/2018
Invoice Period |  |  |  | Initial draw down (as per contract) | Remaining to draw down | 4/1 - 4/15 | 4/16 - 5/15
Invoice # |  |  |  | 75347
Invoice Date |  |  |  | 2018-03-21
Project Manager Approval |  |  |  | 2018-03-27
Board Approval
Check #
Check Date
Original
|  |  | Contract |  |  |  |  | Total | Balance
Deliverable # 1 - Lead Generation Campaign
1 | 1.1 | Pay Per Click Ad Spend | 10000 |  |  | 0 | 187.5 | 187.5 | 10187.5
2 | 1.2 | Campaign Management and Reporting | 10000 |  |  | 500 | 1050 | 1550 | 11550
Deliverable # 1 Subtotal |  |  | 20000
Deliverable # 2 - Two Event Sponsorships
3 | 2.1 | Direct Sponsorship Cost | 17500 |  |  | 0 |  | 0 | 17500
4 | 2.2 | Research and Coordination | 5250 |  |  | 600 | 1050 | 1650 | 6900
Deliverable # 2 Subtotal |  |  | 22750 | 10000 | 8350
Deliverable # 3 - Business Attraction Event
5 | 3.1 | Event Execution Costs | 27500 |  |  | 0 | 0 | 0 | 27500
6 | 3.2 | Planning, Promotion and Coordination | 7500 |  |  | 0 | 1200 | 1200 | 8700
Deliverable # 3 Subtotal |  |  | 35000 | 10000 | 8800
Deliverable # 4 - Lead Follow Up
7 | 4.1 | Create List of Interview Questions | 500 |  |  | 0 | 0 | 0 | 500
8 | 4.2 | Conduct Phone Invterviews with at least 12 Leads | 1250 |  |  | 0 | 0 | 0 | 1250
9 | 4.3 | Reporting | 500 |  |  | 0 | 0 | 0 | 500
Deliverable # 3 Subtotal |  |  | 2250
|  |  | 80000 | 20000 | 17150 | 1100 | 3487.5 | 4587.5 | 84587.5
|  |  | Cumulative |  |  | 1100 | 4587.5
|  |  | Drawdown Amount |  |  | 600 | 2250
|  |  | Amount Due |  |  | 500 | 1237.5