## Invoices
Contract with Luminary Publishing, Inc.
2018 Business Attraction Marketing
4/1/2018 - 12/31/2018
Invoice Period |  |  |  | Initial draw down (as per contract) | Remaining to draw down | 4/1 - 4/15 | 4/16 - 5/15 | 5/16 - 6/15 | 6/16 - 7/15 | 7/16 - 8/15 | 8/16 - 9/15 | 9/16 - 10/15 | 10/16 - 11/15 | 11/16 - 12/15 | 12/15 - 12/31
Invoice # |  |  |  | 75347
Invoice Date |  |  |  | 2018-03-21
Project Manager Approval |  |  |  | 2018-03-27
Board Approval
Check #
Check Date
Original
|  |  | Contract | [14 empty] | Total Amount Contracted | Total Amount Invoiced | Remaining Balance
Deliverable # 1 - Lead Generation Campaign
1 | 1.1 | Pay Per Click Ad Spend | 10000 |  |  | 0 | 187.5 | 500 | 1000 | 1000 | 319.45 | [6 empty] | 10000 | 3006.95 | 6993.05
2 | 1.2 | Campaign Management and Reporting | 10000 |  |  | 500 | 1050 | 1050 | 1050 | 1350 | 600 | 600 | [5 empty] | 10000 | 6200 | 3800
Deliverable # 1 Subtotal |  |  | 20000
Deliverable # 2 - Two Event Sponsorships
3 | 2.1 | Direct Sponsorship Cost | 17500 |  |  | 0 |  | 10000 |  |  | 7500 | [6 empty] | 17500 | 17500 | 0
4 | 2.2 | Research and Coordination | 5250 |  |  | 600 | 1050 | 0 | 1350 | 900 | 600 | 750 | [5 empty] | 5250 | 5250 | 0
Deliverable # 2 Subtotal |  |  | 22750 | 10000 | 0
Deliverable # 3 - Business Attraction Event
5 | 3.1 | Event Execution Costs (time + receipts) | 27500 |  |  | 0 | 0 | 4550.29 | 2889.85 | 1650 | 900 | 5742.71 | [5 empty] | 27500 | 15732.85 | 11767.15
6 | 3.2 | Planning, Promotion and Coordination | 7500 |  |  | 0 | 1200 | 3450 | 2250 | 600 | 0 | [6 empty] | 7500 | 7500 | 0
Deliverable # 3 Subtotal |  |  | 35000 | 10000 | 0
Deliverable # 4 - Lead Follow Up
7 | 4.1 | Create List of Interview Questions | 500 |  |  | 0 | 0 | 0 |  | 500 | 0 | [6 empty] | 500 | 500 | 0
8 | 4.2 | Conduct Phone Invterviews with at least 12 Leads | 1250 |  |  | 0 | 0 | 0 |  | 450 | 450 | 345 | [5 empty] | 1250 | 1245 | 5
9 | 4.3 | Reporting | 500 |  |  | 0 | 0 | 0 |  | 150 | 150 | 195 | [5 empty] | 500 | 495 | 5
Deliverable # 3 Subtotal |  |  | 2250
|  |  | 80000 | 20000 | 0 | 1100 | 3487.5 | 19550.29 | 8539.85 | 6600 | 10519.45 | 7632.71 | 0 | 0 | 0 | 0 | 0 | 80000 | 57429.8 | 22570.2
|  |  | Cumulative |  |  | 1100 | 4587.5 | 24137.79 | 32677.64 | 39277.64 | 49797.09 | 57429.8 | 57429.8 | 57429.8 | 57429.8 | 57429.8 | 57429.8
|  |  | Drawdown Amount |  |  | 600 | 2250 | 16350.29 | 799.71
|  |  | Amount Due |  |  | 500 | 1237.5 | 3200 | 7740.14 | 6600 | 10519.45 | 7632.71 | 0 | 0 | 0 | 0 | 0