AMENDMENT No. 3 TO CONTRACT #2015-00000432

AGREEMENT FOR PROFESSIONAL SERVICES

ULSTER COUNTY ECONOMIC DEVELOPMENT ALLIANCE, INC.

This Amendment No. 3 (“Amendment No. 3”) is effective as of November 1, 2019 (the “Amendment Effective Date”) and entered into by and between the County of Ulster, a municipal corporation and a county of the  State of New York, with principal offices at 244 Fair Street, Kingston, New York 12401 (hereinafter referred to as the “County”) and Ulster County ECONOMIC Development ALLIANCE, INC., a local development corporation formed under the laws of the State of New York, with offices at 244 Fair Street, Kingston, New York 12401 (“UCEDA”) (each, a “Party,” together, the “Parties”).

RECITALS

WHEREAS, the County and UCEDA entered into an Agreement, wherein UCEDA agreed to provide certain economic development services, including administration and oversight of the Ellenville Million Program (hereinafter referred to as the “Program”), which was designed to enhance the economic prosperity of the Village of Ellenville and the Town of Wawarsing based on recommendations form the Ellenville Million Committee, as amended by that certain Amendment No. 1 effective as of August 1, 2016, and that certain Amendment No. 2 effective May 15, 2019 (as amended, the “Agreement”); and

WHEREAS, the Program as originally envisioned comprised nine Program areas, commonly referred to as Components, each of which was allocated an initial fund balance for the purposes of implementing Projects within the Component; and

WHEREAS, after more than 20 months of active promotion and attempts by UCEDA to expend the Component allocations, UCEDA has determined that changes to the original Component allocations and definitions, in a manner consistent with the original goals of the Program, are necessary; and

WHEREAS, based on its experience administering the Program since September, 2015 and on the successes and challenges encountered in implementing the Program as originally designed, UCEDA has proposed recommendations for modification of the Scope of Services included in the Agreement; and

WHEREAS, the County and UCEDA have agreed to amend the terms and conditions of the Agreement to effect the proposed changes to the Scope of Services and to extend the Term, as indicated below.

NOW, THEREFORE, in consideration of the mutual promises set forth herein, the Parties agree as follows:

AGREEMENT

1.  	SCHEDULE A – SCOPE OF SERVICES. Section V of Schedule A of the Agreement is hereby amended to include a new paragraph l, which shall read as follows:

l.	Health Care Sector Capital Assistance: Drawing from the remainder of the unobligated or unused funds from all the other allocations consistent with the original goals of the Ellenville Million Program this new component will be used to provide capital assistance to health care organizations for the delivery of critical health care needs to the Ellenville Community.

2.    All Ellenville Million Program Elements are required to be completed no later than the contract end date of July 1, 2020.

2	SCHEDULE B – FEES, EXPENSES, AND SUBMISSIONS FOR PAYMENT. Section 1 of Schedule B of the Agreement is hereby amended to read as follows:

- UCEDA’s fee for Services to be provided pursuant to this Agreement shall not exceed ONE MILLION AND 00/100 ($1,000,000.00) DOLLARS.  Funds shall be distributed in accordance with the following budget. unallocated funds remaining as of November 1, 2019, shall be reallocated for Health Care Sector Capital Assistance. Any funds remaining after closeout of existing contracts may be allocated to the Health Care Sector Capital Assistance. provided however projects can be completed prior to July 1, 2020.

Expenses incurred for any of the Ellenville Million Program elements after July 1, 2020 will not be reimbursed.

| Ellenville Million Program Component | Original Allocation | Amended Allocation |
| --- | --- | --- |
| Water and Sewer Improvement Projects | $150,000 | $45,000 |
| “Jump Start” Fund | $175,000 | $125,000 |
| Improvement to Outdoor Recreational Opportunities | $150,000 | $174,600 |
| Historic Preservation Projects at the Shadowland Theatre | $75,000 | $75,000 |
| Capital Projects at the Hunt Memorial Building | $100,000 | $100,000 |
| Main Street Improvement Projects | $25,000 | $50,000 |
| Project Management and Grant Writing* | $75,000 | $48,900 |
| Improved Access to High Speed Internet | $150,000 | $75,000 |
| Tourism Marketing Campaign | $100,000 | $151,500 |
| Vocational Training and Workforce Transportation | $0 | $50,000 |
| Grant Matching and Grant Writing Assistance | $0 | $105,000 |
| TOTAL | $1,000,000 | $1,000,000 |

*see exception to billing requirements in section 2 below.

3.	Capitalized terms used but not defined herein shall have the meanings set forth in the Agreement.

4.	Except as expressly set forth herein, the terms and conditions of the Agreement shall continue in full force and effect.

5. 	In the event of a conflict between the Agreement and this Amendment No. 3, the terms and conditions of this Amendment No. 3 shall control.

IN WITNESS WHEREOF, the Parties have caused their duly authorized representatives to enter into this Amendment No. 3, effective as of the Amendment Effective Date.

ULSTER COUNTY PLANNING DEPARTMENT	ULSTER COUNTY ECONOMIC DEVELOPMENT ALLIANCE, INC.

By:   _______________________	By:_______________________

NAME: Dennis Doyle	NAME:

TITLE: Director	TITLE: DATE:_____________________       	DATE:_____________________

ULSTER COUNTY

By:   _______________________

NAME: Edward Jordan

TITLE:	Director of Purchasing

DATE:___________________________